## Sheet1
Sprint | Team Name | Name | Working Days | Holidays | Assigned Points | Sprint Days | Leaves | Planned Items | Delivered Items | User Stories | Bugs | Rollover Points | Rollovers | Delivered Points | Capacity | Ideal Story Points | Product | Velocity | Actual Velocity | Trailing Velocity
17 | The Dragons | Kuldeep Bhati | 10 | 0 | 15 | 10 | 0 | 7 | 6 | 6 | 1 | 2 | 1 | 13 | 10 | 12 | Intrics Dev | 12 | 13 | 12
17 | The Dragons | Karan Dobriyal | 10 | 0 | 10 | 10 | 2 | 8 | 8 | 5 | 3 | 0 | 0 | 10 | 8 | 11 | Intrics Dev | 11 | 10 | 11
17 | The Dragons | Prachi Gupta | 10 | 0 | 7 | 10 | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 7 | 6 | 10 | Intrics Dev | 10 | 7 | 10
17 | The Hawks | Rahul Choudhary | 10 | 0 | 11 | 10 | 0 | 5 | 5 | 5 | 1 | 0 | 0 | 11 | 10 | 10 | Intrics Dev | 10 | 11 | 10
17 | The Hawks | Dinesh Kumar | 10 | 0 | 11 | 10 | 1 | 7 | 7 | 2 | 5 | 0 | 0 | 11 | 9 | 11 | Intrics Dev | 11 | 11 | 11
17 | The Hawks | Utkarsh Singh | 10 | 0 | 11 | 10 | 1 | 6 | 6 | 4 | 2 | 0 | 0 | 11 | 9 | 9 | Intrics Dev | 9 | 11 | 9
17 | The Phoenix | Abhishek Singh | 10 | 0 | 7 | 10 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 7 | 7 | 11 | Intrics Dev | 11 | 7 | 11
17 | The Phoenix | Govinda Ohlyan | 10 | 0 | 11 | 10 | 2 | 6 | 6 | 5 | 1 | 0 | 0 | 11 | 8 | 11 | Intrics Dev | 11 | 11 | 11
17 | The Phoenix | Anup Kishore | 10 | 0 | 11 | 10 | 0 | 5 | 5 | 4 | 1 | 0 | 0 | 11 | 10 | 10 | Intrics Dev | 10 | 11 | 10
17 | The Phoenix | Jeevan Perumalla | 10 | 0 | 11 | 10 | 0 | 4 | 2 | 4 | 0 | 4 | 2 | 7 | 10 | 8 | Intrics Dev | 8 | 7 | 8
17 | Tiger Team | Abdul Ahad | 10 | 0 | 15 | 10 | 1 | 9 | 9 | 9 | 0 | 0 | 0 | 15 | 9 | 13 | Intrics Dev | 13 | 15 | 13
17 | Tiger Team | Suneel Kumar | 10 | 0 | 10 | 10 | 1 | 5 | 4 | 4 | 1 | 2 | 1 | 8 | 9 | 9 | Intrics Dev | 9 | 8 | 9
17 | Tiger Team | Braj Mohan | 10 | 0 | 12 | 10 | 1 | 3 | 2 | 3 | 0 | 2 | 1 | 10 | 9 | 10 | Intrics Dev | 10 | 10 | 10
17 | Tech Titans | Sadhu Pathak | 10 | 0 | 12 | 10 | 1 | 6 | 4 | 3 | 3 | 2 | 2 | 10 | 9 | 11 | Intrics Dev | 11 | 10 | 11
17 | Tech Titans | Rahul Bansal | 10 | 0 | 8 | 10 | 3 | 4 | 4 | 3 | 1 | 0 | 0 | 8 | 7 | 10 | Intrics Dev | 10 | 8 | 10
17 | Tech Titans | Gunjan Karki | 10 | 0 | 11 | 10 | 0 | 10 | 10 | 8 | 2 | 0 | 0 | 11 | 10 | 8 | Intrics Dev | 8 | 11 | 8
16 | The Dragons | Kuldeep Bhati | 10 | 0 | 14 | 10 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 14 | 10 | 11 | Intrics Dev | 11 | 14 | 11
16 | The Dragons | Karan Dobriyal | 10 | 0 | 14 | 10 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 14 | 10 | 11 | Intrics Dev | 11 | 14 | 11
16 | The Dragons | Prachi Gupta | 10 | 0 | 12 | 10 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 12 | 10 | 10 | Intrics Dev | 10 | 12 | 10
16 | The Hawks | Rahul Choudhary | 10 | 0 | 7 | 10 | 3 | 5 | 5 | 5 | 0 | 0 | 0 | 7 | 7 | 11 | Intrics Dev | 11 | 7 | 11
16 | The Hawks | Dinesh Kumar | 10 | 0 | 12 | 10 | 0 | 8 | 8 | 5 | 3 | 0 | 0 | 12 | 10 | 10 | Intrics Dev | 10 | 12 | 10
16 | The Hawks | Utkarsh Singh | 10 | 0 | 8 | 10 | 0 | 5 | 5 | 3 | 2 | 0 | 0 | 8 | 10 | 10 | Intrics Dev | 10 | 8 | 10
16 | The Phoenix | Abhishek Singh | 10 | 0 | 13 | 10 | 0 | 7 | 7 | 5 | 2 | 0 | 0 | 13 | 10 | 11 | Intrics Dev | 11 | 13 | 11
16 | The Phoenix | Govinda Ohlyan | 10 | 0 | 11 | 10 | 0 | 6 | 6 | 5 | 1 | 0 | 0 | 11 | 10 | 10 | Intrics Dev | 10 | 11 | 10
16 | The Phoenix | Anup Kishore | 10 | 0 | 13 | 10 | 0 | 5 | 4 | 4 | 1 | 1 | 1 | 12 | 10 | 8 | Intrics Dev | 8 | 12 | 8
16 | The Phoenix | Jeevan Perumalla | 10 | 0 | 9 | 10 | 0 | 4 | 3 | 3 | 1 | 2 | 1 | 7 | 10 | 9 | Intrics Dev | 9 | 7 | 9
16 | Tiger Team | Abdul Ahad | 10 | 0 | 16 | 10 | 0 | 7 | 5 | 7 | 0 | 4 | 2 | 12 | 10 | 11 | Intrics Dev | 11 | 12 | 11
16 | Tiger Team | Suneel Kumar | 10 | 0 | 12 | 10 | 0 | 7 | 7 | 7 | 0 | 0 | 0 | 12 | 10 | 9 | Intrics Dev | 9 | 12 | 9
16 | Tiger Team | Braj Mohan | 10 | 0 | 8 | 10 | 1 | 4 | 4 | 4 | 0 | 0 | 0 | 8 | 9 | 11 | Intrics Dev | 11 | 8 | 11
16 | Tech Titans | Sadhu Pathak | 10 | 0 | 11 | 10 | 1 | 5 | 5 | 5 | 0 | 0 | 0 | 11 | 9 | 11 | Intrics Dev | 11 | 11 | 11
16 | Tech Titans | Rahul Bansal | 10 | 0 | 10 | 10 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 10 | 10 | 10 | Intrics Dev | 10 | 10 | 10
16 | Tech Titans | Gunjan Karki | 10 | 0 | 10 | 10 | 0 | 7 | 6 | 5 | 2 | 1 | 1 | 9 | 10 | 8 | Intrics Dev | 8 | 9 | 8
15 | The Dragons | Kuldeep Bhati | 10 | 0 | 14 | 10 | 0 | 7 | 6 | 6 | 1 | 2 | 1 | 12 | 10 | 10 | Intrics Dev | 10 | 12 | 10
15 | The Dragons | Karan Dobriyal | 10 | 0 | 12 | 10 | 0 | 7 | 7 | 6 | 1 | 0 | 0 | 12 | 10 | 10 | Intrics Dev | 10 | 12 | 10
15 | The Dragons | Prachi Gupta | 10 | 0 | 10 | 10 | 1 | 5 | 5 | 5 | 0 | 0 | 0 | 10 | 9 | 10 | Intrics Dev | 10 | 10 | 10
15 | The Hawks | Rahul Choudhary | 10 | 0 | 13 | 10 | 0 | 10 | 10 | 6 | 4 | 0 | 0 | 13 | 10 | 10 | Intrics Dev | 10 | 13 | 10
15 | The Hawks | Dinesh Kumar | 10 | 0 | 11 | 10 | 0 | 9 | 9 | 5 | 4 | 0 | 0 | 11 | 10 | 9 | Intrics Dev | 9 | 11 | 9
15 | The Hawks | Utkarsh Singh | 10 | 0 | 13 | 10 | 0 | 6 | 5 | 5 | 1 | 3 | 1 | 10 | 10 | 9 | Intrics Dev | 9 | 10 | 9
15 | The Phoenix | Abhishek Singh | 10 | 0 | 15 | 10 | 1 | 10 | 9 | 5 | 5 | 2 | 1 | 13 | 9 | 11 | Intrics Dev | 11 | 13 | 11
15 | The Phoenix | Govinda Ohlyan | 10 | 0 | 12 | 10 | 1 | 6 | 6 | 6 | 0 | 0 | 0 | 12 | 9 | 10 | Intrics Dev | 10 | 12 | 10
15 | The Phoenix | Anup Kishore | 10 | 0 | 5 | 10 | 6 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 4 | 9 | Intrics Dev | 9 | 2 | 9
15 | The Phoenix | Jeevan Perumalla | 10 | 0 | 9 | 10 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 9 | 10 | 8 | Intrics Dev | 8 | 9 | 8
15 | Tiger Team | Abdul Ahad | 10 | 0 | 11 | 10 | 2 | 6 | 6 | 6 | 0 | 0 | 0 | 11 | 8 | 11 | Intrics Dev | 11 | 11 | 11
15 | Tiger Team | Suneel Kumar | 10 | 0 | 9 | 10 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 9 | 7 | 8 | Intrics Dev | 8 | 9 | 8
15 | Tiger Team | Braj Mohan | 10 | 0 | 10 | 10 | 0 | 8 | 8 | 2 | 6 | 0 | 0 | 10 | 10 | 9 | Intrics Dev | 9 | 10 | 9
15 | Tech Titans | Sadhu Pathak | 10 | 0 | 11 | 10 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 11 | 10 | 10 | Intrics Dev | 10 | 11 | 10
15 | Tech Titans | Rahul Bansal | 10 | 0 | 11 | 10 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 11 | 10 | 10 | Intrics Dev | 10 | 11 | 10
15 | Tech Titans | Gunjan Karki | 10 | 0 | 8 | 10 | 0 | 6 | 6 | 4 | 2 | 0 | 0 | 8 | 10 | 6 | Intrics Dev | 6 | 8 | 6
14 | The Dragons | Kuldeep Bhati | 9 | 1 | 9 | 9 | 0 | 6 | 6 | 4 | 2 | 0 | 0 | 9 | 9 | 10 | Intrics Dev | 10 | 9 | 10
14 | The Dragons | Karan Dobriyal | 9 | 1 | 8 | 9 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 8 | 5 | 10 | Intrics Dev | 10 | 8 | 10
14 | The Dragons | Prachi Gupta | 9 | 1 | 9 | 9 | 1 | 5 | 5 | 4 | 1 | 0 | 0 | 9 | 8 | 10 | Intrics Dev | 10 | 9 | 10
14 | The Hawks | Rahul Choudhary | 9 | 1 | 9 | 9 | 1 | 6 | 6 | 5 | 1 | 0 | 0 | 9 | 8 | 10 | Intrics Dev | 10 | 9 | 10
14 | The Hawks | Dinesh Kumar | 9 | 1 | 9 | 9 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 9 | 9 | 8 | Intrics Dev | 8 | 9 | 8
14 | The Hawks | Utkarsh Singh | 9 | 1 | 7 | 9 | 2 | 3 | 3 | 3 | 1 | 0 | 0 | 7 | 7 | 9 | Intrics Dev | 9 | 7 | 9
14 | The Phoenix | Abhishek Singh | 9 | 1 | 10 | 9 | 0 | 6 | 6 | 3 | 3 | 0 | 0 | 10 | 9 | 11 | Intrics Dev | 11 | 10 | 11
14 | The Phoenix | Govinda Ohlyan | 9 | 1 | 9 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 9 | 9 | 10 | Intrics Dev | 10 | 9 | 10
14 | The Phoenix | Anup Kishore | 9 | 1 | 7 | 9 | 0 | 3 | 3 | 2 | 1 | 0 | 0 | 7 | 9 | 9 | Intrics Dev | 9 | 7 | 9
14 | The Phoenix | Jeevan Perumalla | 9 | 1 | 10 | 9 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 10 | 9 | 9 | Intrics Dev | 9 | 10 | 9
14 | Tiger Team | Abdul Ahad | 9 | 1 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Intrics Dev | 0 | 0 | 0
14 | Tiger Team | Suneel Kumar | 9 | 1 | 6 | 9 | 1 | 3 | 3 | 2 | 1 | 0 | 0 | 6 | 8 | 8 | Intrics Dev | 8 | 6 | 8
14 | Tiger Team | Braj Mohan | 9 | 1 | 11 | 9 | 1 | 5 | 5 | 1 | 9 | 0 | 0 | 11 | 9 | 9 | Intrics Dev | 9 | 11 | 9
14 | Tech Titans | Sadhu Pathak | 9 | 1 | 10 | 9 | 0 | 6 | 6 | 3 | 3 | 0 | 0 | 10 | 9 | 10 | Intrics Dev | 10 | 10 | 10
14 | Tech Titans | Rahul Bansal | 9 | 1 | 10 | 9 | 0 | 5 | 5 | 2 | 3 | 0 | 0 | 10 | 9 | 9 | Intrics Dev | 9 | 10 | 9
14 | Tech Titans | Gunjan Karki | 9 | 1 | 5 | 9 | 2 | 3 | 3 | 3 | 0 | 0 | 0 | 5 | 7 | 7 | Intrics Dev | 7 | 5 | 7